# Contingency Plan

Adopted: [Insert Date]

Approved by:

## I. Purpose

This contingency plan establishes a clear protocol for responding to major disruptions in funding, particularly grant-related income, and provides guidelines for maintaining operations, protecting core services, and making staff-related decisions. It also outlines a chain of command and a decision-making process for emergency scenarios.

## II. Primary Risk Scenario: Grant Funding Reduction or Interruption

### A. Risk Scenarios

- Grant funding is frozen or withdrawn unexpectedly.

- Grants are not renewed or are delayed.

- Key grantor(s) or partner(s) (e.g., GLRI, MISGP, state or federal programs) discontinues or restricts funding.

- Overall operating revenue falls below the threshold for core staff retention.

### B. Immediate Impacts

- Reduction in staff hours.

- Potential layoffs or non-renewals of seasonal and full-time positions.

- Inability to cover operational or payroll expenses.

- Delays in program delivery and reporting.

## III. Chain of Command and Emergency Decision-Making Flow

### A. Leadership Roles

Coordinator / Executive Director:

First point of response.

Evaluates financial status and staff funding.

Prepares recommendation for action.

WRISC Board of Directors:

Reviews Coordinator’s recommendation.

Provides consensus via email or emergency meeting.

Authority on grant and funding-related decisions.

Dickinson Conservation District Board (Fiscal Agent):

Final authority on all employment-related decisions.

May call a special meeting to expedite decisions.

WRISC Accountant/Treasurer – Finances currently handled by DCD Fiscal Agent:

DCD District Manager and WRISC Coordinator - Reviews availability of undesignated funds.

Assists in assessing short-term cash flow solvency.

## IV. Emergency Action Flow Chart

- Trigger: Major Grant Disruption or Budget Shortfall Identified

- Step 1: WRISC Coordinator Assesses Impact and Drafts Action Plan

- Step 2: Coordinator Seeks Email Consensus from WRISC Board

- Step 3: Upon Consensus, Formal Recommendation Sent to DCD Board

- Step 4: DCD Board Votes on Staff and Budget Actions

- Step 5: Communication Plan Activated to Notify Staff, Partners, and Funders

## V. Emergency Staffing Actions

### A. Reduction of Hours (Furlough or Hour Cutbacks)

- Coordinator may initiate temporary hour reductions for seasonal/hourly employees.

- Full-time position changes require WRISC Board consensus and DCD Board approval.

### B. Reduction in Force (Layoffs)

- Coordinator prepares staff reduction proposal.

- WRISC Board provides consensus.

- DCD Board makes final determination.

### C. Communication Protocol

- All employment decisions must be communicated in writing to affected staff.

- Public or partner communications coordinated through the WRISC Coordinator.

## VI. Financial Sustainability Actions

### A. Use of Undesignated Funds

- These funds may be used for shortfalls, insurance, tax obligations, and critical functions.

- WRISC Board has preemptively approved the use of up to 20% of undesignated funds during critical funding response to cover payroll shortfalls not eligible for reimbursement

### B. Operational Prioritization

- Prioritize:

- Payroll for key staff

- Insurance, withholding

- Compliance, taxes

- Minimum field operations.

### C. Revenue Generation

- Pursue fee-for-service contracts.

- Seek emergency/bridge grants.

- Launch short-term fundraising appeal.

## VII. Long-Term Resilience Planning

- Maintain reserve fund equal to 3 months of core operations.

- Diversify funding portfolio.

- Forecast and prepare for grants 6–12 months in advance.

- Review plan annually.

## VIII. Plan Review and Updates

Reviewed by WRISC Board: Annually in Q4.

Maintained by: WRISC Coordinator and Fiscal Agent.

Next Review Date: [Insert 12 months after adoption]

## IX. Additional Risk Scenarios

Beyond funding reductions, WRISC faces other potential risks that could impact operations. These scenarios should be monitored and included in annual contingency reviews.

### Financial Risks

- Delayed reimbursements from grants or partners leading to cash flow problems.

- Loss of major donor or partner funding unrelated to grants.

- Cost overruns on projects (e.g., equipment repairs, fuel costs).

- Audit findings or compliance penalties impacting future funding eligibility.

### Operational Risks

- Staff turnover or sudden loss of key personnel (e.g., Coordinator resignation or illness).

- Volunteer shortages impacting program delivery during peak field season.

- Equipment failure or loss (e.g., watercraft, vehicles, sprayers critical for fieldwork).

- Inability to access field sites due to landowner disputes, weather, or legal restrictions.

### Environmental/Ecological Risks

- Natural disasters (flooding, wildfires, storms) damaging habitats, equipment, or access.

- Emergence of new invasive species requiring immediate, unfunded response.

- Severe weather impacting field season (shortened work windows, safety concerns).

### Governance & Compliance Risks

- Loss of 501(c)(3) status due to compliance failures.

- Conflicts of interest or ethical issues among board or staff members.

- Data security breach of sensitive information (donors, partners, landowners).

- Failure to meet grant reporting requirements leading to contract terminations or ineligibility.

### Reputational Risks

- Negative media coverage or public controversy (e.g., treatment methods, herbicide use).

- Partner organization disputes or withdrawal of collaboration agreements.

- Community backlash against invasive species removal efforts.

### Programmatic Risks

- Mission drift due to overreliance on restricted grants.

- Policy changes at state or federal level affecting funding streams or priorities.

- Emergent competing priorities reducing support for invasive species work.

### Technological Risks

- Failure of key digital systems (GIS databases, volunteer management platforms).

- Cybersecurity incidents (ransomware, phishing attacks targeting nonprofit emails).

## X. Risk Prioritization Matrix

WRISC will maintain a risk matrix to prioritize contingency planning. The matrix categorizes risks by likelihood and impact, focusing mitigation efforts on high-likelihood, high-impact events.

| Impact ↓ / Likelihood → | Low | Medium | High | Critical |
| --- | --- | --- | --- | --- |
| Low |  |  |  |  |
| Moderate |  |  |  |  |
| High |  |  |  |  |
| Severe |  |  |  |  |

## Appendix: Emergency Decision-Making Flowchart

The following visual flowchart illustrates the chain of command and decision-making process during funding disruptions: